## Slide 1: ETE Test Deck (Wireline & MFE)
4 Jun 2026
81739588
81739588
81739588
83682664
Notes: p

## Slide 2
Jun’26 Release Dashboard - Summary
ETE - Schedule Status
Program | 26.06
Wireline | 15
MFE | 8
ETE Billing | 3
Total | 25
Scope baselined 15 | 
ETE Approved Schedule | 15
Awaiting approval ST | 0
Not Scope baselined : 0 | 
ETE Billing - Schedule Status
Chart: 
| wireline | MFE | ETE Billing
Column1 | 15 | 8 | 2
Scope baselined : 1 | 
ETE Approved Schedule | 0
Awaiting approval ST | 1
Not Scope baselined : 2 | 
Scope baselined : 5 | 
ETE Approved Schedule | 4
Awaiting approval ST | 1
Not Scope baselined : 3 | 
MFE - Schedule Status

## Slide 3: Jun’26 Release - Overall ETE Testing (Wireline)
Chart: 
Status Summary | 
BLUE | 1
GREEN | 7
AMBER | 6
RED | 1
GREY | 0
Total | 15
Chart: 
| Black | Blue | Green | Amber | Red | Purple
0
Chart: 
| Black | Blue | Green | Amber | Red | Purple
0
Project ID
Chart: 
 | 1 | 7 | 6 | 1
Project ID | Strategic Initiative | UFD# | Project Name | Planned Start Date | Planned End Date | Actual Start Date | Test Steps | Test Steps Executed % | TS Status | 
 |  |  |  |  |  |  | Planned % |  | This Week | Last Week
433732 | True North | 5615 | ASEoD Deprecation Phase 2B | 4/2/2026 | 7/17/2026 | 4/2/2026 | 42.2% | 22.9% | Red | Red
437318 | ABS - Maintenance | 8926 | ASEoD Speed Floors | 4/27/2026 | 6/5/2026 | 4/27/2026 | 87.1% | 79.2% | Amber | Amber
437600 | ABS - Revenue Generation - Value Added Services | 7424 | DDNIS | 4/30/2026 | 6/28/2026 | 4/30/2026 | 27.7% | 16.5% | Amber | Amber
437501 | ABS - Mandates | 7312 | CGW453 on ABF DD | 5/12/2026 | 7/2/2026 | 5/12/2026 | 38.5% | 25.0% | Amber | Green
437501 | ABS - Revenue Generation - Wireline Growth | 7312 | Wavelength Cycle Time | 4/27/2026 | 6/5/2026 | 4/27/2026 | 92.9% | 78.6% | Amber | Red
437672 | ABS - Modernization - Common Capabilities | 7511 | BCLM Migration - AVPN & BVOIP | 5/11/2026 | 6/26/2026 | 5/11/2026 | 37.8% | 18.8% | Amber | Amber
 |  |  | BCLM Migration - ADI | 4/27/2026 | 6/26/2026 | 4/28/2026 | 60.6% | 61.1% | Amber | Red
437315 | ABS - Mandates | 7774 | IPFlex FCC 911 Compliance | 4/27/2026 | 6/5/2026 | 4/27/2026 | 96.6% | 98.6% | Green | Green
437318 | ABS - Maintenance | 7905 | ADIVB Missing Port Charge fix | 5/4/2026 | 6/5/2026 | 5/4/2026 | 94.4% | 88.9% | Green | Green
437496 | ABS - Modernization - Sales Tooling& Transformation | 7414 | Cloud Runner - Embedded base MVP2 | 5/4/2026 | 6/5/2026 | 5/4/2026 | 90.97% | 81.09% | Green | Amber
437414 | ABS - Modernization - Sales Tooling& Transformation | 4714 | AIAB with ABV Voice Priority - ASF | 5/6/2026 | 6/19/2026 | 5/6/2026 | 50.86% | 73.65% | Green | Green
 |  |  | AIAB with ABV Voice Priority - BC flow | 5/19/2026 | 6/29/2026 | 5/19/2026 | 20.3% | 3.1% | Amber | Green
Planned | Current Actuals | Overall Status
72.87% | 67.43% | Amber

## Slide 4: Jun’26 Release - Overall ETE Testing (Wireline)
Chart: 
Chart: 
| Black | Blue | Green | Amber | Red | Purple
0
Chart: 
| Black | Blue | Green | Amber | Red | Purple
0
Project ID
Project ID | Strategic Initiative | UFD# | Project Name | Planned Start Date | Planned End Date | Actual Start Date | Test Steps | Test Steps Executed % | TS Status | 
 |  |  |  |  |  |  | Planned % |  | This Week | Last Week
437318 | ABS - Maintenance | 7692 | ADI Wan IP | 4/27/2026 | 6/5/2026 | 4/27/2026 | 100.0% | 100.0% | Green | Green
437427 | Network - Operational Enhancements | 4454 | NNI_EATM | 5/11/2026 | 6/2/2026 | 5/11/2026 | 100.0% | 100.0% | Green | Green
437315 | ABS - Mandates | 7774 | IPFlex FCC Compliance NextGen 911 Order Phase-1 | 5/12/2026 | 5/29/2026 | 5/12/2026 | 100.0% | 100.0% | Green | Green
437643 | ABS - Product Growth Council | 7721 | ABF Enhanced Internet - ETE (MACD & SA) | 4/9/2026 | 5/23/2026 | 4/9/2026 | 100.0% | 100.0% | Green | Green
437318 | ABS - Maintenance | 7962 | ADI IGLOO Quick Hit | 5/4/2026 | 5/24/2026 | 5/4/2026 | 100.0% | 100.0% | Blue | Blue

## Slide 5: Jun’26 Release - ETE Testing (Wireline)
Project ID | Strategic Initiative | UFD# | Project Name | Planned Start Date | Planned End Date | Actual Start Date | Test Steps Planned % | Test Steps Passed % | TS Status
433732 | True North | 5615 | ASEoD Deprecation Phase 2B | 4/2/2026 | 7/17/2026 | 4/2/2026 | 42.2% | 22.9% | Red
Project ID | Overall Status | Critical Highlights | Open Defects / Blockers
433732 | ETE Testing Total TCs: 44 Blocked: 10 In Progress: 1 On hold: 3 Execution Completed: 5 Not Started: 23 Descoped: 2 | Note: Flow Verification Testing completed 100% on 6/3 ETE testing Scope: 44 TCs (New start, Supp, Change, Add, Remove, Disconnect, VLAN) Sales Originating app: BC ETE testing resumed from 4/2 1 TCs (Add EVC) In Progress (EVC Activation In Progress) 10 TCs (6 Change UNI, 3 Add EVC, 1 Change EVC) blocked by defects PINV Defect# 517288 (Created on 6/4); TC14 - Change UNI COS MACD- getProductsAPI is failing with 503 service temporarily available in SDW for the change port workflow; PINV team is creating a ticket for the Sentry team as only test and stage environments are down; Blocker for all IR MACDs PINV Defect# 517281 (Created on 6/4); getConfiguredProductListDetails API and getConfiguredProductDetails API is failing in UAT3; Blocker for all IR MACDs. Topology adapter issue. PINV Test and Stage env is down PINV team is investigating SDW Defect# 516976 (Created on 6/3); Change UNI MACD IR - Dates are not being passed in sequence from SDW to CANOPI in ExternallyActivatedUni Payload; Retest Blocked by PINV Defect# 517281 BC Defect# 516456 (Created on 6/2); Add DD on IEVC. Review Order page is not showing the Asset ID for Internal EVC which is selected for MACD; Retest Failed. ST retest to be retried post PINV defect# 517281 resolution BC Defect# 517041 (Created on 6/3); billAccountNumber is not passing under MasterOrder payload from BC; ETA 6/4 EOD BC Defect# 512065 (Created on 5/19); Add EVC Leg to a Port - Unable to submit order as it shows 'You don't have valid EVC/iEVC' for Existing Active Port which was pulled from Network Inventory Page; Retest Blocked by PINV Defect# 517281 | PINV(2)-No ETA SDW(1)-Retest Blocked BC(3)-1 Retest Failed, 1 ETA 6/4 EOD, 1 Retest Blocked

## Slide 6: Jun’26 Release - ETE Testing (Wireline)
Project ID | Strategic Initiative | UFD# | Project Name | Planned Start Date | Planned End Date | Actual Start Date | Test Steps Planned % | Test Steps Passed % | TS Status
437501 | Tech Enablement - Development | 7312 | Wavelength Cycle Time | 4/27/2026 | 6/5/2026 | 4/27/2026 | 91.1% | 78.6% | Amber
437318 | Tech Enablement - Development | 7905 | ASEoD Speed Floors | 4/27/2026 | 6/5/2026 | 4/27/2026 | 87.1% | 79.2% | Amber
Project ID | Overall Status | Critical Highlights | Open Defects / Blockers
437501 | Total TCs: 4 Blocked: 4 | Project in Amber since testing was majorly blocked by USRP defect# 516406 since 6/1. Defect retest currently stuck due to ACMS PON creation not working. Triage in progress with ACMS, EOT, USRP ETE Testing Scope: 4 EPLSWAN New Start TCs Sales originating app: ECAP Testing started as per plan on 4/2; 4 TCs blocked by USRP Defect# 516406 (Created on 6/1); Orders are failed with fatal error and rejected from carrier as ACMS is not mapping the address properly; Defect retest currently stuck due to ACMS PON creation not working. Triage in progress with ACMS, EOT, USRP Non-Blocker Defects EOXP Defect# 516063 (Created on 5/30); Address validation status is not reflecting in EOX UI; ETA was 6/3. Awaiting update EOT Defect# 511902 (Created on 5/19); Get ECAP request button is not returning all values for ECAP request id  ETA 7/11 EO Defect# 517008 (Created on 6/3); Fallout email is not triggered in EO; No ETA | USRP(1)-Retest
437318 | Total TCs: 10 Blocked: 4 Execution Completed: 6 | Project in Forced Amber since testing is blocked by OCX Defect# 516064 which had an ETA of 6/4. Awaiting update ETE Testing Scope: 10 ASEoD TCs (3 New Starts, 2 Ordering & Provisioning, 5 MACDs) Code impacted applications: BC, EDF Testing started as per plan on 4/27 6 TCs (3 New Start TCs, 2 O&P, 1 MACD Regression) Execution Completed 4 MACD TCs blocked by OCX Defect# 516064 (created on 5/30) Original Speed Field data is missing in AssetLIST API in BC for ASEOD Change Speed Order UAT ENV; ETA of 6/4 missed. Working bridge in progress between OCX, EDF and ETE teams Non-Blocker Defects BC Defect# 516223 (Created on 6/01) Qualify API is failing for LNS SITEs in ASEOD Change CIR in BC UAT env; Need ETA | OCX(1)-No ETA

## Slide 7: Jun’26 Post Release - ETE Testing (Wireline)
Project ID | Strategic Initiative | UFD# | Project Name | Planned Start Date | Planned End Date | Actual Start Date | Test Steps Planned % | Test Steps Passed % | TS Status
437672 | ABS - Modernization - Common Capabilities | 7511 | BCLM Migration - ADI | 4/27/2026 | 6/26/2026 | 4/28/2026 | 60.6% | 61.1% | Amber
 |  |  | BCLM Migration - AVPN & BVOIP | 5/11/2026 | 6/26/2026 | 5/11/2026 | 34.6% | 16.4% | Amber
Project ID | Overall Status | Critical Highlights | Open Defects / Blockers
437672 | Total TCs: 13 Blocked: 1 On hold: 6 In Progress: 4 Not Started: 2 | Project in Forced Amber since testing is majorly blocked by ADOPT Defect# 516565 with no ETA ETE Testing Scope: 13 ADI New Start TCs Sales originating app: ASF Testing started as per plan on 4/27 1 TCs blocked by ADOPT Defect# 516565 (Created on 6/3); Missing details in ISOD causing OMX decomposition to remain pending; Retest 6 TCs on hold due to Potential blocker ADOPT Defect# 516565 Defects in Retest ABR/OBE/BGW Defect# 515508 (Created on 5/28); Biller ID: PL sent from A&BR which should be UP when ABR retrieve Service MCN triplet; Triage in progress; Retest COMS Defect# 515106 (Created on 5/27); Getting “External Discount ID Invalid” issue in BGW; Moved from ADOPT to COMS on 6/1; Retest BCLM Defect# 514257 (Created on 5/25); Countersign email not received; Retest | ADOPT(1)-Retest
437672 | Total TCs: 12 In Progress: 7 Not Started: 5 | Project in Amber since testing was majorly blocked by BCLM defect# 515216 between 5/27-6/2 , BVOP code from COMS-BCLM for contract generation delivered on 5/27 (Original ETA of 5/11 missed) ETE Testing Scope: 12 New Starts (8 AVPN, 4 BVOIP) Sales originating app: ASF Testing started as per plan on 5/11 7 TCs (4 AVPN, 3 BVOIP) In Progress - BCLM Defect# 515216 (Created on 5/27); Countersign email not received; Retest | BCLM(1)-Retest

## Slide 8: Jun’26 Post Release - ETE Testing (Wireline)
Project ID | Strategic Initiative | UFD# | Project Name | Planned Start Date | Planned End Date | Actual Start Date | Test Steps Planned % | Test Steps Passed % | TS Status
437600 | AT&T Business | 7424 | DDNIS | 4/30/2026 | 6/28/2026 | 4/30/2026 | 27.7% | 16.5% | Amber
437501 | ABS - Mandates | 7312 | CGW453 on ABF DD | 5/12/2026 | 7/2/2026 | 5/12/2026 | 38.5% | 25.0% | Amber
Project ID | Overall Status | Critical Highlights | Open Defects / Blockers
437600 | Total TCs: 14 Blocked: 3 In Progress: 2 Execution Completed: 1 Not Started: 12 | Project is Amber since testing is majorly blocked by defects/Issues NIS Defects 510274 & 516449 with no ETA ASF code delivered on 6/1 (Original ETA of 4/30 missed) 12 Not Started MACD TCs dependent on the New Start completion (4 MACD TCs out of the 12 cannot be started though NS would complete due to SDW code unavailability until 6/9) ETE currently mocking up the payload data into SDW and continuing with the testing until ASF orders are provided ASF order received for 1 New Start on 6/3. 1 New Start TC In Progress Daily working bridge set up by ATT LPM to progress with the testing ETE testing Scope: 19 TCs (5 New Starts, 6 Change, 1 SA, 1 Admin change, 2 Cancel, 4 New Add) Sales Originating app: ASF Testing started as per plan on 4/30 New Start Execution blocked by defects NIS Defect# 510274 (Created on 5/13); DDNIS Create Customer Failure. Retest Failed on 6/1. No ETA yet NIS Defect# 516449 (Created on 6/3); Admin Setup is complete, but SDW action 'admin-setup-completed' failed; No ETA | NIS(2)-No ETA
437501 | Total TCs: 24 In Progress: 5 Execution Completed: 4 Not Started: 15 | Project is Amber since testing was majorly blocked by IOMIP & EF defects until 6/2 ETE testing Scope: 24 ABF TCs (NS, Amend, Cancel, Disconnect, Add, Change, SA) Sales Originating App: ASF, LS-CRM Testing Started as per plan on 5/12 5 TCs In Progress; No major blockers | 

## Slide 9: Jun’26 Release - ETE Testing (Wireline)
Project ID | Strategic Initiative | UFD# | Project Name | Planned Start Date | Planned End Date | Actual Start Date | Test Steps Planned % | Test Steps Passed % | TS Status
437315 | ABS - Mandates | 7774 | IPFlex FCC 911 Compliance | 4/27/2026 | 6/5/2026 | 4/27/2026 | 96.6% | 98.6% | Green
437318 | ABS - Maintenance | 7905 | ADIVB Missing Port Charge fix | 5/4/2026 | 6/5/2026 | 5/4/2026 | 94.4% | 88.9% | Green
437496 | ABS - Modernization - Sales Tooling& Transformation | 7414 | Cloud Runner - Embedded base MVP2 | 5/4/2026 | 6/5/2026 | 5/4/2026 | 90.97% | 81.09% | Green
Project ID | Overall Status | Critical Highlights | Open Defects / Blockers
437315 | Total TCs: 10 Blocked: 1 Execution Completed: 6 Completed: 3 | ETE Testing Scope: 10 TCs (2 New Starts, 4 Change, 4 MACD) Code impacted applications: SPP, EDF, INSTAR, ASOC Sales Originating app: Testing started as per plan on 4/27 Last Change TC blocked by ACVP Defect# Defect# 517064 (Created on 6/3); Fallout Error occurred in ABV – TN Activation V3 in ABV Add TN MACD order; UR Ticket# UR0126103 raised for this issue. No ETA | ACVP(1)-No ETA
437318 | Total TCs: 2 In Progress: 1 Execution Completed: 1 | ETE Testing Scope: 2 ADI MACD TCs Sales Originating app: Testing started as per plan on 5/4 Last TC In Progress (Bill trigger to BGW in progress) | 
437496 | Total TCs: 8 Execution Completed: 4 In Progress: 1 Blocked: 3 | ETE Testing Scope: 8 TCs (5 Add Site, 1 Add DD, 1 Cancel, 1 Supp CRDD) Sales Originating app: 3 Add Site TCs blocked by ASF/PINV/C360 Defect# 516926 (Created on 6/3); Installation Charge mismatch between Quote Screen and Invoice | ASF/PINV/C360(1)-No ETA

## Slide 10: Jun’26 Release - ETE Testing (Wireline)
Project ID | Strategic Initiative | UFD# | Project Name | Planned Start Date | Planned End Date | Actual Start Date | Test Steps Planned % | Test Steps Passed % | TS Status
437414 | ABS - Modernization - Sales Tooling& Transformation | 4714 | AIAB with ABV Voice Priority - ASF flow | 5/6/2026 | 6/19/2026 | 5/6/2026 | 50.68% | 73.65% | Green
 |  |  | AIAB with ABV Voice Priority - BC flow | 5/19/2026 | 6/29/2026 | 5/19/2026 | 20.3% | 3.1% | Amber
Project ID | Overall Status | Critical Highlights | Open Defects / Blockers
437414 | Total TCs: 14 Blocked: 3 Execution Completed: 8 In Progress: 1 Not Started: 2 | ETE Testing Scope: 14 ABV TCs (NS, Supp, MACD, Disconnect) Testing started as per plan on 5/6 3 New Start TCs blocked by defects ACVP Defect# 515972 (Created on 5/29); Fixed. Need new order from ASF to retest ACVP Defect# 515711 (Created on 5/29); ETA 6/5 UB Defect# 517154 (Created on 6/3); No ETA | ACVP(2)-1 No ETA, 1 Retest UB(1)-No ETA
437414 | Total TCs: 6 Blocked: 1 Not Started: 5 | ETE Testing Scope: 6 TCs (Add Site, MACD, Supp) Testing started as per plan on 5/6 1 TC (Add Site) blocked by SSP/OE Defect# 513083 (Created on 5/21) Foundational data is missing for the order. ETA 6/8 Potential blocker for the Not Started TCs | SSP(1)-6/8